## Sheet1
Project Name:Farm Shop |  | Presented by: Mahitha Avula |  | Date: | 2023-06-13
| Internal | $/hour | Internal | External | $/hour | External | Total | Non-labor $ | Total Cost
WBS Categories | Labor |  | $ Total | Labor |  | $ Total | Labor
1. Initiating | 25 | 90 | 2225 |  |  | $- | 2225 |  | 2225
2. Planning | 10 | 66 | 660 |  |  | $- | 660 |  | 660
3. Executing |  |  | $- |  |  | $- | $- |  | $-
3.1 Course design and development |  |  | $- |  |  | $- | $- |  | $-
3.1.1 Supplier management training | 8 | 65 | 520 | 10 | 150 | 1500 | 2020 | 500 | 2520
3.1.2 Negotiating skills training | 6 | 70 | 420 | 10 | 180 | 1800 | 2220 | 500 | 2720
3.1.3 Project management training | 8 | 55 | 440 | 10 | 200 | 2000 | 2440 | 500 | 2940
3.1.4 Software applications training | 6 | 85 | 510 | 10 | 200 | 2000 | 2510 | 3000 | 5510
3.2 Course administration | 10 | 70 | 700 | 10 | 250 | 2500 | 3200 | 2000 | 5200
3.3.Course evaluation | 30 | 80 | 2400 |  |  | $- | 2400 |  | 2400
3.4 Stakeholder communications | 10 | 90 | 900 |  |  | $- | 900 |  | 900
4. Monitoring and Controlling | 25 | 65 | 1625 |  |  | $- | 1625 |  | 1625
5. Closing | 25 | 60 | 1500 |  |  | $- | 1500 |  | 1500
Subtotal | [8 empty] | 28200
Reserves | [5 empty] | $- |  |  | 1800
Total | 163 |  | 11900 | 50 | 980 | 9800 | 21700 | 4800 | 30000
Assumptions: We are expecting our overall budget around 25000$ with reserves at 25 % which accounts to total of 30000$