## Sheet1
Risk Register For Farm Shop Date: 06/16/2023
Project Name: Farm Shop
ID No. | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status
100 | 1 | Scope Creep | If there is a continuous expansion of the project scope beyond the agreed-upon boundaries, it can lead to dissatisfaction among stakeholders and difficulties in managing the project effectively. Scope creep can occur due to unclear requirements or frequent changes in project objectives. | Scope risk | Unclear or changing scope requirements | Product owner's frequent modification requests and Failure to manage scope changes effectively | Risk Mitigation. | Project Manager | High | High | Prediction
201 | 2 | Rise in Budget | Accurate estimation of the budget and effective execution of the project strategy are crucial for successful project delivery. | Financial/PeopleRisk | Inaccurate budget estimations | Increase in salaries or unforeseen expenses | Risk Acceptance. | Financial Manager | High | Medium | Prediction
235 | 3 | Natural Disasters | Natural disasters are unpredictable events that can have a significant impact on the performance of the project. These risks cannot be resolved and are unavoidable. | Financial Risk. | Absence of a comprehensive disaster recovery plan | Lack of preparedness for natural disasters | Risk Acceptance. | Organization | Low | High | Anticipated
312 | 4 | Schedule Delays | Failure to effectively manage time and ensure timely completion of daily tasks can have detrimental consequences for the project, potentially resulting in client dissatisfaction. Proper time management is crucial to avoid unnecessary burdens and ensure the smooth progress of the project. | Process Risk/Schedule Risk | Inadequate project planning or unforeseen obstacles | Inaccurate time estimation, unexpected issues or delay /Unable to finish the scheduled work on time. | Risk Mitigation. | Project Manager & Team | Medium | High | Expected
320 | 5 | Vendor dependency | Relying heavily on a single vendor for critical project components or services poses the risk of disruption if the vendor experiences issues or fails to deliver as expected.Diversifying vendor options and establishing contingency plans can help mitigate this risk. | Supply Risk | Overreliance on a single vendor. | Vendor failure or inability to meet requirements. | Risk Mitigation. | Project Manager | Medium | High | Predicted
334 | 6 | Product Shelf Life | Failure to effectively manage product shelf life can lead to product spoilage, wastage, and financial losses. | Market Risk and Financial Risk. | Inaccurate inventory management, insufficient rotation practices, lack of monitoring | Expired products, increased product losses, negative customer experience | Risk Acceptance. | Program Manager. | Low | High | Anticipated
456 | 7 | Legal compilance | Failure to comply with legal regulations and requirements can result in penalties, lawsuits, or reputational damage for the organization. It is crucial to ensure that the project adheres to all applicable laws and regulations. | Legal Risk | Lack of understanding of legal requirements. | Non-compliance with legal regulations. | Risk Mitigation. | Project Manager/Legal department | Medium | High | Prediction
574 | 8 | Server support | Server many not support many number of users to use the website at the same time | Maintainence Risk. | Present servers not able to support huge number of users at a time | Application /website hang or slow response | Risk Acceptance. | Program Manager/Developer. | Low | High | Expected
675 | 9 | Quality Control Issues | Problems that arised in maintaining the desired standard of product quality, including inconsistent grading, product defects, or contamination. These issues can have negative consequences such as customer complaints, product returns, and damage to the farm shop's reputation | Operational Risk | Inadequate quality control processes or lack of employee training | Product defects, contamination, inconsistent grading | Risk Mitigation. | Quality Manager | Medium | High | Expected
789 | 10 | Seasonal Variability | The success of a farm shop is heavily influenced by seasonal fluctuations in demand and availability of agricultural products. Managing inventory, marketing strategies, and customer expectations during different seasons is crucial to mitigate the risk of low sales or insufficient supply. | Operational Risk | Seasonal changes in agricultural production | Fluctuating customer demand | Risk Mitigation. | Project Manager&Team | Medium | Medium | Expected